## Client Side
Dilsboro Client Side Bugs and Issues:
Issue # | Reported By: | Brief Description | Platform | OS version | Long Description | Replicated | Solution | Codebase solution added to:
1 | Tim Heaton | Uncategorized map should center towards icon (it starts in the middle of nowhere and you have to zoom out to see it) | Droid |  |  |  | Not really an issue, the uncategorized category was the promotion category and there was only 1 poi in it. The map centers on Dillsboro as a whole
2 | Tim Heaton | If you select an Image from the Images or go to the website link and push the back button and then go to the Directions or Turn-By-Turn page, it will not load | Droid |  |  |  | This was solved last semester in re-factoring the code.
3 | Tim Heaton | Data_Catagories when using the publishing admin tool on CLAWS, throws an exception | General |  |  |  | This was solved last semester by pulling the Category_X.js files out of the Data_Category.js file.
4 | Tim Heaton | Push Pin Using movile device back button, only between the first and second page | droid |  |  |  | this was solved last semester in re-factoring the code.
5 | Tim Heaton | Lanscape view does not reform properly, happens when you try to switch device to landscape view after loading is complete | I touch |  |  |  | I don't remember this bug and I tried replicating it on the Touch without result.
6 | Tim Heaton | If there is no image available the image dropdown list should be hidden | General |  |  |  | Not an issue, but a suggestion to maybe bring up and see whether it should be taken into consideration.
7 | Micheal Halpin | When the shops category is clicked “http://localhost:61962 Unable to reach load Category Data. Please try again later” | General |  |  |  | Solved, removed pretty print from code | 9_1_12_Dillsboro
8 | Daniel Parris | Droid back button causes errors on map page | Droid |  | When a user loads a category and then uses the droid back button and reloads a new category or the same one, it does not show the map nor the application back or home buttons. | Yes, 9_19_12 on droid/ Mitch
| Micheal Halpin | Droid Razor causes the second image to dissapear in photoswipe | Driod Razor |  | When sliding through the photo gallery some of the images dissapear then reapper after swiping a few more times | yes, 12/11/12 on droid razor/ britt/mitch

## Server Side
Dilsboro Server Side Bugs and Issues:
Reported By: | Brief Description | Platform | OS version | Long Description | Replicated | Solution | Codebase solution added to:
Tim Heaton | In some situations the PrettyPrint code yields a JSON file that breaks the client-side code | General |  |  |  | Solved, Removed pretty print from deployed 9/1/12 version

## deployment log
Dillsboro Deployment Log
Name | Deployment Date | notes
9_1_12_Dillsboro
Dillsboro_12_4_12 | 2012-12-04 | On mobile test
Dillsboro_12_3_12 | 2012-12-03 | on live site
Dillsboro_12_4_12 | 2012-12-05 | on live site

## Change Log
Dillsboro Client Side Code Change log
Name | Change | Notes
Dillsboro_12_4_12 | 1. Made toolbar bigger in footer
Dillsboro_12_3_1 | 1. Added an ID to the categories <ul> tag created in categories.js. Also added a small bit of code to take out any spaces that may be in the ID. 2.Changed map zoom to 14. poiList_Map.js 3.Added an icon for Special Events to images folder. 4.Hide special events from categories page using 'main.css' (hidden using #SpecialEvents{display:none};) 5. added special events to index.htlm statically 6. added new style sheet and backgroun images. 7. added new index.html page, moved old one to categories.html. 8. added toolbar to footer. 9. added connect tab to index.html with links to social media pages | most current up to date version
Dillsboro_10_24_12 | 1. Switched the order of the html on the MapList_Main.htm file to show list page first map page second. 2. In the MapList_Main.js file, I changed the mapListPageInfo.CurrentPage to "List"
Dillsboro_9_26_12 | 1. Added maplist code for the map list transistion, 2. Removed old list.htm and map.htm and replaced them with MapList_Main.htm. 3. Removed the JS filesfor the old list.htm and map.htm and added, MapList_List.js, MapList_Main.js, and MapList_Map.js
Dillsboro_9_1_12 | none | bug free